## Örnek
Month | Focus | Product | Supply (Advisors/Businesses) | Growth | Revenue | KPI
M1 | MVP | Basic platform live | 20 advisors | 10 SEO content | 0 | 50 users
M2 | MVP | Booking system | 50 advisors | 30 content + outreach | First sales | 200 users
M3 | Launch | Payment integration | 70 advisors | SEO + LinkedIn | $1K | 500 users
M4 | Growth | User dashboard | 100 advisors | Referral system | $3K | 1K users
M5 | Growth | Improvements | 120 advisors | Content scale | $5K | 2K users
M6 | PMF | Stabilization | 150 advisors | Organic growth | $10K | Retention focus
M7 | Scale | New features | 200 advisors | New city prep | $15K | 3K users
M8 | Scale | Expansion | 250 advisors | City launch | $25K | 5K users
M9 | Scale | Optimization | 300 advisors | Partnerships | $40K | 7K users
M10 | Expansion | Perks layer | 350 advisors | B2B deals | $60K | 10K users
M11 | Expansion | Automation | 400 advisors | Scale channels | $80K | 15K users
M12 | Seed Ready | Full system | 500 advisors | Global growth | $100K | 20K users

## Sayfa3
Phase | Category | Task | Priority | Status | Output
MVP | Supply | Create 100 advisor list | High | To Do | Liste hazır
MVP | Supply | Reach out (100 advisors) | High | To Do | DM gönderildi
MVP | Supply | Onboard first 20 advisors | High | To Do | 20 onboard
MVP | Supply | Expand to 50 advisors | High | To Do | 50 advisor
MVP | Content | Write 10 SEO articles | High | To Do | 10 içerik
MVP | Content | Publish blog | High | To Do | Blog live
MVP | Content | Distribute in communities | High | To Do | Trafik başladı
MVP | Growth | LinkedIn posting (weekly) | Medium | To Do | Görünürlük
MVP | Growth | WhatsApp group sharing | High | To Do | User akışı
MVP | Growth | Early users onboarding (50) | High | To Do | İlk kullanıcılar
MVP | Revenue | Define pricing model | High | To Do | Model hazır
MVP | Revenue | Test first paid booking | High | To Do | İlk gelir
Launch | Supply | Reach 100 advisors | High | To Do | Scale supply
Launch | Growth | SEO scale (30+ content) | High | To Do | Trafik artışı
Launch | Growth | Referral system activate | High | To Do | Kullanıcı büyüme
Launch | Partnership | Start local partnerships | Medium | To Do | İlk işbirliği
Launch | Revenue | Optimize conversion | High | To Do | Daha fazla satış
Launch | Ops | User feedback loop | High | To Do | İyileştirme
Launch | Ops | Customer support flow | Medium | To Do | Destek sistemi

## Sayfa2
1. sütun | Phase | Category | Task | Priority | Status | Output
| MVP | Setup | Project repo setup (GitHub) | High | To Do
| MVP | Setup | Database schema (users, advisors, bookings) | High | To Do
| MVP | Auth | User signup/login (email + Google) | High | To Do
| MVP | Profiles | Advisor profile create/edit | High | To Do
| MVP | Profiles | User profile basic | Medium | To Do
| MVP | Listing | Advisor listing page | High | To Do
| MVP | Search | Filter/search advisors | High | To Do
| MVP | Booking | Booking request system | High | To Do
| MVP | Booking | Calendar availability basic | Medium | To Do
| MVP | Payment | Stripe integration | High | To Do
| MVP | Payment | Commission logic (% cut) | High | To Do
| MVP | Notification | Email notifications | Medium | To Do
| MVP | Admin | Basic admin panel | High | To Do
| MVP | Content | Blog system (CMS basic) | Medium | To Do
| MVP | SEO | SEO structure (URL, meta) | High | To Do
| Launch | UX | Improve onboarding flow | High | To Do
| Launch | UX | Advisor onboarding form optimize | High | To Do
| Launch | Performance | Page speed optimization | High | To Do
| Launch | Analytics | Google Analytics setup | High | To Do
| Launch | Analytics | Event tracking (signup, booking) | High | To Do
| Launch | Security | Basic security checks | High | To Do
| Launch | Mobile | Mobile optimization | High | To Do
| Launch | Support | Chat/support system | Medium | To Do
| Launch | Referral | Referral system basic | Medium | To Do
| Launch | Scaling | Server scaling readiness | Medium | To Do